## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Makireddy Bala Bhavya | 2026-02-16 | User login error during authentication | Milestone 1 (Weeks 1–2) | Self | Logical | Fixed authentication logic in login module | 2026-02-18 | Closed | Login issue resolved successfully
2 | Makireddy Bala Bhavya | 2026-03-02 | Cart items not updating correctly | Milestone 2 (Weeks 3–4) | Self | Logical | Updated cart state management logic | 2026-03-04 | Closed | Cart updates working correctly
3 | Makireddy Bala Bhavya | 2026-03-16 | Wishlist add/remove not working | Milestone 3 (Weeks 5–6) | Self | UI | Corrected wishlist add/remove functionality | 2026-03-18 | Closed | Wishlist functioning properly
4 | Makireddy Bala Bhavya | 2026-03-30 | Product images not loading properly | Milestone 3 (Weeks 5–6) | Self | UI | Updated product image paths and URLs | 2026-04-01 | Closed | Product images loading correctly
5 | Makireddy Bala Bhavya | 2026-04-02 | Recommendation system showing duplicate items | Milestone 4 (Weeks 7–8) | Self | Performance | Added duplicate filtering in recommendation system | 2026-04-03 | Closed | Duplicate recommendations removed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others